## MacAllan Option 1
FINANCIAL ANALYSIS OF OSC PROJECT - OPTION 1 - MACALLAN
Planning Parameters
Sales per year | 40000
Avg Income per skier-day | 60
Operating fixed Cost per year | 900000
| 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | Total
Marketing Costs
Preparation of Materials |  | 70000 | [15 empty] | 70000
Establishing Agreements with various agents around the UK |  | 20000 | [15 empty] | 20000
Marketing Campaign Launch |  | 200000 | [15 empty] | 200000
Company Soliciting
Purchase of Land | 6000000 | [16 empty] | 6000000
Planning documentation & Agreement | 100000 | [16 empty] | 100000
Architectural Design & Construction
Architectural Designing | 250000 | [16 empty] | 250000
Construction of Access Road A (MacAllan) |  | 500000 | [15 empty] | 500000
Construction of Skilift 1 (Chairlift c) |  | 838000 | [15 empty] | 838000
Construction of Skilift 2 (Chairlift d) |  | 576000 | [15 empty] | 576000
Construction of Skilift 3 (Chairlift b) |  | 708000 | [15 empty] | 708000
Construction of Office/Shop Foundations |  | 50000 | [15 empty] | 50000
Construction of Office/Shop Structures |  | 100000 | [15 empty] | 100000
Construction of Office/Shop Fittings |  | 30000 | [15 empty] | 30000
Construction of Airthrey Restaurant Foundations |  | 100003.2 | [15 empty] | 100003.2
Construction of Airthrey Restaurant Structures |  | 200000 | [15 empty] | 200000
Construction of Airthrey Restaurant Fittings |  |  | 100000 | [14 empty] | 100000
Inspections
Health & Safety Inspections |  |  | 20000 | [14 empty] | 20000
Lift Inspections |  |  | 30000 | [14 empty] | 30000
Trainings |  |  | 20000 | [14 empty] | 20000
Overheads (Project Management & Communication) |  | 600000 | [15 empty] | 600000
Total Investment | 6350000 | 3992003.2 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10512003.2
Operating Fixed Costs |  |  | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 13500000
Total Costs | 6350000 | 3992003.2 | 1070000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 24012003.2
Income |  |  | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 36000000
Profit | -6350000 | -3992003.2 | 1330000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 11987996.8
Cumulative Profit | -6350000 | -10342003.2 | -9012003.2 | -7512003.2 | -6012003.2 | -4512003.2 | -3012003.2 | -1512003.2 | -12003.2 | 1487996.8 | 2987996.8 | 4487996.8 | 5987996.8 | 7487996.8 | 8987996.8 | 10487996.8 | 11987996.8
ROI | 1.1592
Discount Rate | 10.39%
Year | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
PV Factor | 1 | 0.90588 | 0.82062 | 0.74338 | 0.67341 | 0.61003 | 0.55261 | 0.5006 | 0.45348 | 0.4108 | 0.37214 | 0.33711 | 0.30538 | 0.27664 | 0.2506 | 0.22701 | 0.20565
NPV | -6.35 | -3.6163 | 1.0914 | 1.1151 | 1.0101 | 0.91505 | 0.82892 | 0.7509 | 0.68023 | 0.6162 | 0.55821 | 0.50567 | 0.45807 | 0.41496 | 0.3759 | 0.34052 | 0.30847 | 0.0034324
IRR | 10.4%

## uCan Option 1
FINANCIAL ANALYSIS OF OSC PROJECT - OPTION 1 - UCAN
Planning Parameters
Sales per year | 40000
Avg Income per skier-day | 60
Operating fixed Cost per year | 900000
| 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | Total
Marketing Costs
Preparation of Materials |  | 70000 | [15 empty] | 70000
Establishing Agreements with various agents around the UK |  | 20000 | [15 empty] | 20000
Marketing Campaign Launch |  | 200000 | [15 empty] | 200000
Company Soliciting
Purchase of Land | 6000000 | [16 empty] | 6000000
Planning documentation & Agreement | 100000 | [16 empty] | 100000
Architectural Design & Construction
Architectural Designing | 250000 | [16 empty] | 250000
Construction of Access Road A (uCan) |  | 800000 | [15 empty] | 800000
Construction of Skilift 1 (Chairlift c) |  | 838000 | [15 empty] | 838000
Construction of Skilift 2 (Chairlift d) |  | 576000 | [15 empty] | 576000
Construction of Skilift 3 (Chairlift b) |  | 708000 | [15 empty] | 708000
Construction of Office/Shop Foundations |  | 50000 | [15 empty] | 50000
Construction of Office/Shop Structures |  | 100000 | [15 empty] | 100000
Construction of Office/Shop Fittings |  | 30000 | [15 empty] | 30000
Construction of Airthrey Restaurant Foundations |  | 100003.2 | [15 empty] | 100003.2
Construction of Airthrey Restaurant Structures |  | 200000 | [15 empty] | 200000
Construction of Airthrey Restaurant Fittings |  |  | 100000 | [14 empty] | 100000
Inspections
Health & Safety Inspections |  |  | 20000 | [14 empty] | 20000
Lift Inspections |  |  | 30000 | [14 empty] | 30000
Trainings |  |  | 20000 | [14 empty] | 20000
Overheads (Project Management & Communication) |  | 500000 | [15 empty] | 500000
Total Investment | 6350000 | 4192003.2 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10712003.2
Operating Fixed Costs |  |  | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 13500000
Total Costs | 6350000 | 4192003.2 | 1070000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 24212003.2
Income |  |  | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 36000000
Profit | -6350000 | -4192003.2 | 1330000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 11787996.8
Cumulative Profit | -6350000 | -10542003.2 | -9212003.2 | -7712003.2 | -6212003.2 | -4712003.2 | -3212003.2 | -1712003.2 | -212003.2 | 1287996.8 | 2787996.8 | 4287996.8 | 5787996.8 | 7287996.8 | 8787996.8 | 10287996.8 | 11787996.8
ROI | 1.1182
Discount Rate | 9.968%
Year | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
PV Factor | 1 | 0.90936 | 0.82693 | 0.75197 | 0.68381 | 0.62183 | 0.56546 | 0.5142 | 0.46759 | 0.42521 | 0.38667 | 0.35162 | 0.31975 | 0.29076 | 0.26441 | 0.24044 | 0.21864
NPV | -6.35 | -3.812 | 1.0998 | 1.128 | 1.0257 | 0.93274 | 0.84819 | 0.77131 | 0.70139 | 0.63781 | 0.58 | 0.52743 | 0.47962 | 0.43614 | 0.39661 | 0.36066 | 0.32797 | 0.091325
IRR | 10.11%

## MacAllan Option 2
FINANCIAL ANALYSIS OF OSC PROJECT - OPTION 2 - MACALLAN
Planning Parameters
Sales per year | 80000
Avg Income per skier-day | 70
Operating fixed Cost per year | 2400000
| 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | Total
Marketing Costs
Preparation of Materials |  | 70000 | [15 empty] | 70000
Establishing Agreements with various agents around the UK |  | 20000 | [15 empty] | 20000
Marketing Campaign Launch |  | 200000 | [15 empty] | 200000
Company Soliciting
Purchase of Land | 12000000 | [16 empty] | 12000000
Planning documentation & Agreement | 200000 | [16 empty] | 200000
Architectural Design & Construction
Architectural Designing | 500000 | [16 empty] | 500000
Construction of Access Road A (MacAllan) |  | 500000 | [15 empty] | 500000
Construction of Access Road B (MacAllan) |  | 1000000 | [15 empty] | 1000000
Construction of Skilift 1 (Chairlift c) |  | 838000 | [15 empty] | 838000
Construction of Skilift 2 (Chairlift d) |  | 576000 | [15 empty] | 576000
Construction of Skilift 3 (Chairlift b) |  | 708000 | [15 empty] | 708000
Construction of Skilift 4 (Chairlift b) |  | 708000 | [15 empty] | 708000
Construction of Skilift 5 (Chairlift h) |  | 555000 | [15 empty] | 555000
Construction of Skilift 6 (Chairlift b) |  | 708000 | [15 empty] | 708000
Construction of Skilift 7 (Chairlift c) |  | 838000 | [15 empty] | 838000
Construction of Office/Shop Foundations |  | 50000 | [15 empty] | 50000
Construction of Office/Shop Structures |  | 100000 | [15 empty] | 100000
Construction of Office/Shop Fittings |  | 30000 | [15 empty] | 30000
Construction of Airthrey Restaurant Foundations |  | 100003.2 | [15 empty] | 100003.2
Construction of Airthrey Restaurant Structures |  | 200000 | [15 empty] | 200000
Construction of Airthrey Restaurant Fittings |  |  | 100000 | [14 empty] | 100000
Construction of Lossburn Restaurant Foundations |  | 249996.8 | [15 empty] | 249996.8
Construction of Lossburn Restaurant Structures |  |  | 300003.2 | [14 empty] | 300003.2
Construction of Lossburn Restaurant Fittings |  |  | 150000 | [14 empty] | 150000
Construction of Balquharn Restaurant Foundations |  | 299995.2 | [15 empty] | 299995.2
Construction of Balquharn Restaurant Structures |  |  | 350003.2 | [14 empty] | 350003.2
Construction of Balquharn Restaurant Fittings |  |  | 180000 | [14 empty] | 180000
Inspections
Health & Safety Inspections |  |  | 40000 | [14 empty] | 40000
Lift Inspections |  |  | 70000 | [14 empty] | 70000
Trainings |  |  | 40000 | [14 empty] | 40000
Overheads (Project Management & Communication) |  | 1140000 | [15 empty] | 1140000
Total Investment | 12700000 | 8890995.2 | 1230006.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22821001.6
Operating Costs |  |  | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 36000000
Total Costs | 12700000 | 8890995.2 | 3630006.4 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 58821001.6
Income |  |  | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 84000000
Profit | -12700000 | -8890995.2 | 1969993.6 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 25178998.4
Cumulative Profit | -12700000 | -21590995.2 | -19621001.6 | -16421001.6 | -13221001.6 | -10021001.6 | -6821001.6 | -3621001.6 | -421001.6 | 2778998.4 | 5978998.4 | 9178998.4 | 12378998.4 | 15578998.4 | 18778998.4 | 21978998.4 | 25178998.4
ROI | 1.1662
Discount Rate | 10.24%
Year | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
PV Factor | 1 | 0.9071 | 0.82284 | 0.7464 | 0.67706 | 0.61416 | 0.55711 | 0.50536 | 0.45841 | 0.41583 | 0.3772 | 0.34216 | 0.31037 | 0.28154 | 0.25539 | 0.23166 | 0.21014
NPV | -12.7 | -8.0651 | 1.621 | 2.3885 | 2.1666 | 1.9653 | 1.7828 | 1.6171 | 1.4669 | 1.3306 | 1.207 | 1.0949 | 0.99319 | 0.90093 | 0.81723 | 0.74132 | 0.67245 | 0.00082121
IRR | 10.24%

## uCan Option 2
FINANCIAL ANALYSIS OF OSC PROJECT - OPTION 2 - UCAN
Planning Parameters
Sales per year | 80000
Avg Income per skier-day | 70
Operating fixed Cost per year | 2400000
| 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | Total
Marketing Costs
Preparation of Materials |  | 70000 | [15 empty] | 70000
Establishing Agreements with various agents around the UK |  | 20000 | [15 empty] | 20000
Marketing Campaign Launch |  | 200000 | [15 empty] | 200000
Company Soliciting
Purchase of Land | 12000000 | [16 empty] | 12000000
Planning documentation & Agreement | 200000 | [16 empty] | 200000
Architectural Design & Construction
Architectural Designing | 500000 | [16 empty] | 500000
Construction of Access Road A (uCan) |  | 800000 | [15 empty] | 800000
Construction of Access Road B (uCan) |  | 1300000 | [15 empty] | 1300000
Construction of Skilift 1 (Chairlift c) |  | 838000 | [15 empty] | 838000
Construction of Skilift 2 (Chairlift d) |  | 576000 | [15 empty] | 576000
Construction of Skilift 3 (Chairlift b) |  | 708000 | [15 empty] | 708000
Construction of Skilift 4 (Chairlift b) |  | 708000 | [15 empty] | 708000
Construction of Skilift 5 (Chairlift h) |  | 555000 | [15 empty] | 555000
Construction of Skilift 6 (Chairlift b) |  | 708000 | [15 empty] | 708000
Construction of Skilift 7 (Chairlift c) |  | 838000 | [15 empty] | 838000
Construction of Office/Shop Foundations |  | 50000 | [15 empty] | 50000
Construction of Office/Shop Structures |  | 100000 | [15 empty] | 100000
Construction of Office/Shop Fittings |  | 30000 | [15 empty] | 30000
Construction of Airthrey Restaurant Foundations |  | 100003.2 | [15 empty] | 100003.2
Construction of Airthrey Restaurant Structures |  | 200000 | [15 empty] | 200000
Construction of Airthrey Restaurant Fittings |  | 100000 | [15 empty] | 100000
Construction of Lossburn Restaurant Foundations |  | 249996.8 | [15 empty] | 249996.8
Construction of Lossburn Restaurant Structures |  | 300003.2 | [15 empty] | 300003.2
Construction of Lossburn Restaurant Fittings |  |  | 150000 | [14 empty] | 150000
Construction of Balquharn Restaurant Foundations |  | 299995.2 | [15 empty] | 299995.2
Construction of Balquharn Restaurant Structures |  | 350003.2 | [15 empty] | 350003.2
Construction of Balquharn Restaurant Fittings |  |  | 180000 | [14 empty] | 180000
Inspections
Health & Safety Inspections |  |  | 40000 | [14 empty] | 40000
Lift Inspections |  |  | 70000 | [14 empty] | 70000
Trainings |  |  | 40000 | [14 empty] | 40000
Overheads (Project Management & Communication) |  | 1050000 | [15 empty] | 1050000
Total Investment | 12700000 | 10151001.6 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23331001.6
Operating Costs |  |  | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 36000000
Total Costs | 12700000 | 10151001.6 | 2880000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 59331001.6
Income |  |  | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 84000000
Profit | -12700000 | -10151001.6 | 2720000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 24668998.4
Cumulative Profit | -12700000 | -22851001.6 | -20131001.6 | -16931001.6 | -13731001.6 | -10531001.6 | -7331001.6 | -4131001.6 | -931001.6 | 2268998.4 | 5468998.4 | 8668998.4 | 11868998.4 | 15068998.4 | 18268998.4 | 21468998.4 | 24668998.4
ROI | 1.0796
Discount Rate | 9.841%
Year | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
PV Factor | 1 | 0.91041 | 0.82884 | 0.75458 | 0.68698 | 0.62543 | 0.56939 | 0.51838 | 0.47194 | 0.42965 | 0.39116 | 0.35612 | 0.32421 | 0.29516 | 0.26872 | 0.24464 | 0.22272
NPV | -12.7 | -9.2415 | 2.2544 | 2.4147 | 2.1983 | 2.0014 | 1.8221 | 1.6588 | 1.5102 | 1.3749 | 1.2517 | 1.1396 | 1.0375 | 0.94452 | 0.8599 | 0.78286 | 0.71272 | 0.021991
IRR | 9.857%